## Sheet1
Gannt Chart - Implementation
This chart is based upon Plastics for Peru being a registered charity within the uk for three years, with this being the case, it can therfore receive charitable grants from the government and commence the day after the facility is assembled. Purchasing and shipping will take 17-22 days and building the solution will take 1 week as this task is outsourced
[6 empty] | 2021-01-01 | [6 empty] | 2021-01-08 | [6 empty] | 2021-01-15 | [6 empty] | 2021-01-22 | [6 empty] | 2021-01-29 | [6 empty] | 2021-02-05 | [6 empty] | 2021-02-12
[6 empty] | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22
Cost($) | Resources | Risks and Safety | Task | Start Date | Duration | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
£-75 | 5 litter pickers | high masses of plastic needing to be carried | Collection of plastic | 2021-01-01 | 10 | bar: F to S
|  |  | buy equipment form collecting plastic | 2021-01-01 | 2 | bar: F to S
|  |  | employ employees from local areas | 2021-01-03 | 3 | bar: S to T
|  |  | physically collect plastic | 2021-01-11 | 5 | bar: W to S
£-120 | lorry,employees/volunteers | manouvering large lorrys through areas with poor road | Transport Plastic Waste | 2021-01-11 | 1 | bar: M
|  | infrastructure especially in Piedritas | Back to Lobitos site | bar: M
£0 | employees/volunteers, shredder,furnace, moulds | process involves many risks in the form of heat,shredding and toxins | manufacture stage one items | 2021-01-12 | 18 | bar: T to F
£0 | employees/volunteers, stall/market | no major risks | donate/sell stage one items | 2021-01-30 | 2 | bar: S to S
£0 | employees/volunteers, shredder,furnace, moulds | process involves many risks in the form of heat,shredding and toxins | manufacture stage two and one items | 2021-02-01 | 20 | bar: M to S
£+45 | employees/volunteers, stall/market | no major risks | donate/sell stage two and one items | 2021-02-20 | 2 | bar: S to M
| employees/volunteers, stall/market | no major risks | donate/sell stage two items | 2021-02-07 | 4
main task
sub sections of main task
The bottom two stages will constantly repeat moving up a stage until we reach the final stage,stage 5. During this process we will continue to manufacture all previous stages items and predict it will take around 1 month to implement a stage with each new stage starting on the 1st of the new month after the first stage. This slow implementation is vital to
ensuring a slow but steady rise of our businees and allows us to focus on manufacturing core items while introducing more intricate designs. To ensure the quality of all products we will be benchmarking them to a quality checklist. An item will need to receive a score of 100% to pass our quality test, which should ensure all products are of a uniform high standard.
| Hire builders | Ship the fencing, solar panels, molds and machines | Contruct:
| Build machines |  | Solar panels and electrical work
| Purchase molds |  | Fencing
| Hire one expert |  | Machines
| Buy bins and other items for collection point |  | Collection point
Install bins
Recruit locals to learn and create items