## Sheet1
Task | Start Date | Duration
Team Contract | 2020-09-25 | 3
Initial ideas + research | 2020-09-28 | 6
grading and choosing final soultion | 2020-10-05 | 5
inital research on final design | 2020-10-10 | 2
research collection on delegated tasks | 2020-10-12 | 18
creating poster | 2020-10-30 | 21
writing individual parts of 1st draft | 2020-10-30 | 21
review poster and submission | 2020-11-21 | 6
finalise each section of report | 2020-11-27 | 3
review report and submission | 2020-11-30 | 2
44099